## Sheet1
|  | Team A3 |  |  | Scrum Cycle 1 |  |  | Tuesday October 5th - Friday October 14th |  |  | Last Update: 10/5/2021
Task (Prioritized) | Backlog item | Work Unit | Person(s) Responsible | # of People | Task Detail | Start Date | Due Date | Actual End Date | Estimated Time(hours) | Actual Time (hours) | Success Criteria | Obstacles | Results/Status
1 | N/A | Complete notable system improvement form | Michael Merritt | 1 | Write the notable system improvement | 2021-10-05 | 2021-10-05 | 2021-10-05 | 1 | 1 | The team and team manager approve |  | Completed
2 | Menu Navigation | Review code | William Siri | 1 | Review the code related to the current menu navigation | 2021-10-05 | 2021-10-08 | 2021-10-05 | 0.5 | 0.5 | Understanding of the code |  | Completed
3 |  | Implement a software solution |  |  | Implement the software solution |  |  |  | 1 | 0.5 | Test ID TC-08 passes |  | Completed
4 |  | Complete test case |  |  | Use the TC-08 test plan to confirm the code is working properly |  |  |  | 0.5 | 0.5 | Test ID TC-08 passes |  | Completed
5 |  | Commit and push code to GitHub |  |  | When the code passes test case TC-08, write a detailed commit message and push the code to GitHub |  |  |  | 0.5 | 0.5 | Code is successfully pushed to GitHub | Slight difficulty linking to the git repository and pushing to the correct branch | Completed
6 | Level 5 looping | Review code | Michael Merritt | 1 | Locate and review the code for transitioning between levels, specifically for level 5 | 2021-10-06 | 2021-10-12 | 2021-10-12 | 1 | 2 | Understanding of the code | A lot of functions across multiple files were used to manage screens | Completed
7 |  | Implement a software solution |  |  | Implement the software solution to have the level 5 goal lead to the main menu |  |  |  | 2 | 1.5 | Test ID TC-04 passes |  | Completed
8 |  | Verify fix |  |  | Use the TC-04 test plan to confirm the code is working properly |  |  |  | 0.5 | 0.5 | Test ID TC-04 passes |  | Completed
9 |  | Commit and push code to GitHub |  |  | When the code passes test case TC-04, write a detailed commit message and push the code to GitHub |  |  |  | 0.5 | 0.5 | Code is successfully pushed to GitHub |  | Completed
10 | Improve Instructions Screen | Review code | Jonathan Mason | 1 | Review the code related to the instructions screen | 2021-10-06 | 2021-10-12 | 2021-10-12 | 2 | 0.5 | Understanding of the code |  | Completed
11 |  | Implement a software solution |  |  | Implement the software solution |  |  |  | 2 | 0.5 | Test ID TC-05 passes |  | Completed
12 |  | Verify fix |  |  | Use the TC-05 test plan to confirm the code is working properly |  |  |  | 0.5 | 0.5 | Test ID TC-05 passes |  | Completed
13 |  | Commit and push code to GitHub |  |  | When the code passes test case TC-05, write a detailed commit message and push the code to GitHub |  |  |  | 0.5 | 0.5 | Code is successfully pushed to GitHub |  | Completed
14 | Fixing Level Collisions | Fixing Level Collisions | Omar Rosario | 1 | Review the code related to a level. | 2021-10-05 | 2021-10-12 | 2021-10-12 | 2 | 2 | Understanding of the code | Finding where the implemented code for avatar and level collisions are | Completed
15 |  | Implement a software solution |  |  | Implement the software solution |  |  |  | 3 | 0.5 | Test ID TC-01 passes |  | Completed
16 |  | Verify fix |  |  | Use the TC-01 test plan to confirm the code is working properly |  |  |  | 0.5 | 0.5 | Test ID TC-01 passes |  | Completed
17 |  | Commit and push code to GitHub |  |  | When the code passes test case TC-01, write a detailed commit message and push the code to GitHub |  |  |  | 0.5 | 0.5 | Code is successfully pushed to GitHub |  | Completed
18 | N/A | Merge code into master branch on GitHub | Michael Merritt | 1 | Merge all complete and working code into the master branch | 2021-10-12 | 2021-10-12 | 2021-10-12 | 1 | 1 | The code is successfully merged into the master branch |  | Completed
19 | N/A | Create presentation | All team members | 4 | Create a presentation on the progress made during the scrum cycle | 2021-10-13 | 2021-10-13 | 2021-10-13 | 3 | 3 | The presentation satifies all sections of the grading rubric |  | Completed
20 | N/A | Complete individual postmortems | All team members | 4 | Complete individual postmortems on Scrum Sprint 1 | 2021-10-14 | 2021-10-14 | 2021-10-15 | 1 | 1 | All questions answer as outlined in the ScrumPostMortem.pdf on Blackboard |  | Completed
21 | N/A | Submit team postmortems | Michael Merritt | 1 | Submit the team's postmortems to the OneDrive | 2021-10-14 | 2021-10-14 | 2021-10-15 | 0.5 | 0.5 | All postmortems are complete and located in the OneDrive |  | Completed
22 | N/A | Update backlog | Michael Merritt | 1 | Update the backlog | 2021-10-15 | 2021-10-15 | 2021-10-15 | 0.5 | 1 | The backlog is updated |  | Completed
[8 empty] | Total | 23.5 | 18.5
|  | Team A3 |  |  | Scrum Cycle 2 |  |  | Tuesday October 15th - Friday October 29th
Task (Prioritized) | Backlog item | Work Unit | Person(s) Responsible | # of People | Task Detail | Start Date | Due Date | Actual End Date | Estimated Time(hours) | Actual Time (hours) | Success Criteria | Obstacles | Results/Status
1 | N/A | Complete notable system improvement form | Michael Merritt | 1 | Write the notable system improvement | 2021-10-19 | 2021-10-19 | 2021-10-19 | 1 | 1 | The team and team manager approve |  | Completed
2 | Create mute button | Study current code | Omar Rosario | 1 | Study code required to implement enchancement/bug fix | 2021-10-19 | 2021-10-26 | 2021-10-26 | 1 | 1 | Understand and be able to explain the code required to implement enchancement/bug fix |  | Completed
3 |  | Implement software solution |  |  | Implement software solution |  |  |  | 3 | 5 | Implement software solution without errors | Dealing with small bugs | Completed
4 |  | Complete test case from other team member |  |  | Conduct TC-02 |  |  |  | 0.5 | 0.5 | Achieve a passing verdict on TC-02 |  | Completed
5 |  | Comment code where applicable |  |  | Describe function of each implemented section of code |  |  |  | 0.5 | 0.5 | Each section of code is described |  | Completed
6 | Restructure level 3 | Learn how to use a level designer | Michael Merritt | 1 | Read the documentation on how to use the level designer | 2021-10-19 | 2021-10-26 | 2021-10-26 | 2 | 1 | Understand and be able to explain how to use the level designer without causing issues on other levels |  | Completed
7 |  | Create a level 3 mockup |  |  | Design level 3 improvements before adding the improvements to the level designer |  |  |  | 1 | 1 | A level 3 mockup is designed and proposed |  | Completed
8 |  | Create level 3 in the level designer |  |  | Use the level designer to restructure level 3 based on the mockup |  |  |  | 1.5 | 1 | The tiles in level 3 are adjusted according to the mockup proposed |  | Completed
9 |  | Replace enemies on level 3 |  |  | Add more enemies to the redesigned level |  |  |  | 2.5 | 3 | The enemies all spawn in correct locations on the map | I tried to make a custom enemy for level 3, but didn't like the result and scrapped the idea | Completed
10 |  | Complete test case from other team member |  |  | Have another team member test the code with the associated test case |  |  |  | 0.5 | 0.5 | The team member testing the feature is able to pass TC-03 |  | Completed
11 |  | Comment code where applicable |  |  | Place comments in the code where applicable |  |  |  | 0.5 | 0.5 | Each section of the code is described clearly |  | Completed
12 | Improve player movement | Study the current code | Jonathan Mason, William Siri | 2 | Read through and gain and understanding of the legacy code that involves the jumping mechanic | 2021-10-19 | 2021-10-26 | 2021-10-26 | 1 | 1 | Understand and be able to explain the code required to implement enchancement/bug fix |  | Completed
13 |  | Attacking in the air | Jonathan Mason |  | Allow users to attack while in the air |  |  |  | 4 | 4 | The player is able to attack while jumping | Difficulty getting it to look and feel good to the end user. | Completed
14 |  | Implement varrying jump height | William Siri |  | Cause the player's jump height to vary based on whether the user taps or holds the spacebar |  |  |  | 4 | 4 | The player will jump to a specified height based on how long the spacebar is held |  | Completed
15 |  | Get both functions tested and approved | Jonathan Mason, William Siri |  | Have another team member test the code with the associated test case |  |  |  | 0.5 | 0.5 | The team member is able to pass TC-07 |  | Completed
16 | N/A | Merge code into master branch on GitHub | Michael Merritt | 1 | Merge all complete and working code into the master branch | 2021-10-26 | 2021-10-26 | 2021-10-27 | 1 | 1 | The code is successfully merged into the master branch | We wanted to see if we could perfect some of the features, so we pushed back testing and merging. We also were dissatisfied with the attack in air, so we chose not to merge it yet. | Completed
17 | N/A | Create presentation | All team members | 4 | Create a presentation on the progress made during the scrum cycle | 2021-10-26 | 2021-10-26 | 2021-10-27 | 3 | 3 | The presentation satifies all sections of the grading rubric |  | Completed
18 | N/A | Complete individual postmortems | All team members | 4 | Complete individual postmortems on Scrum Sprint 1 | 2021-10-29 | 2021-10-29 | 2021-10-29 | 1 | 1 | All questions answer as outlined in the ScrumPostMortem.pdf on Blackboard |  | Completed
19 | N/A | Submit team postmortems | Michael Merritt | 1 | Submit the team's postmortems to the OneDrive | 2021-10-29 | 2021-10-29 | 2021-10-29 | 0.5 | 0.5 | All postmortems are complete and located in the OneDrive |  | Completed
20 | N/A | Update backlog | Michael Merritt | 1 | Update the backlog | 2021-10-29 | 2021-10-29 | 2021-10-29 | 0.5 | 0.5 | The backlog is updated |  | Completed
[8 empty] | Total | 28.5 | 29.5
|  | Team A3 |  |  | Scrum Cycle 3 |  |  | Tuesday October 29th - Friday November 12th
Task (Prioritized) | Backlog item | Work Unit | Person(s) Responsible | # of People | Task Detail | Start Date | Due Date | Actual End Date | Estimated Time(hours) | Actual Time (hours) | Success Criteria | Obstacles | Results/Status
1 | N/A | Complete notable system improvement form | Michael Merritt | 1 | Write the notable system improvement | 2021-11-02 | 2021-11-02 | 2021-11-02 | 1 | 1 | The team and team manager approve |  | Completed
2 | Fix space bar double bound | Study current code | Omar Rosario | 1 | Study code required to implement enchancement/bug fix | 2021-11-02 | 2021-11-09 | 2021-11-04 | 1 | 0.5 | Understand and be able to explain the code required to implement enchancement/bug fix |  | Completed
3 |  | Implement software solution |  |  | Separate jump and interact feature from spacebar key |  |  | 2021-11-04 | 3 | 0.5 | Spacebar key is used to jump. Another key is used to interact with the game enviornment |  | Completed
4 |  | Complete test case from other team member |  |  | Have another member complete TC-09 |  |  | 2021-11-09 | 0.5 | 0.5 | Achieve a passing verdict on test case |  | Completed
5 |  | Comment code where applicable |  |  | Describe function of each implemented section of code |  |  | 2021-11-05 | 0.5 | 0.5 | Each section of code is described |  | Completed
6 | Relocate narrative screen | Study current code | Omar Rosario | 1 | Study code required to implement enchancement/bug fix | 2021-11-02 | 2021-11-09 | 2021-11-03 | 1 | 0.5 | Understand and be able to explain the code required to implement enchancement/bug fix |  | Completed
7 |  | Implement software solution |  |  | Relocate narrative screen so it will appear before the player can play the game |  |  | 2021-11-03 | 3 | 2 | Narrative screen appears before the gameplay starts and appears when player selects Level One |  | Completed
8 |  | Complete test case from other team member |  |  | Have another team member complete the TC-10 |  |  | 2021-11-09 | 0.5 | 0.5 | Achieve a passing verdict on test case |  | Completed
9 |  | Comment code where applicable |  |  | Describe function of each implemented section of code |  |  | 2021-11-05 | 0.5 | 0.5 | Each section of code is described |  | Completed
10 | Add level completion feedback | Find and gain an understanding of the level clearing code | Michael Merritt | 1 | Read the documentation on level clearing, the gold box, and screen transitions | 2021-11-02 | 2021-11-09 | 2021-11-09 | 2 | 1 | Understand and be able to explain how the gold box at the end of the level functions |  | Completed
11 |  | Propose a solution to make the goal clearer |  |  | Decide on the visual/audio/logical changes to the systems in place to improve the clarity of the gold box |  |  |  | 1 | 1 | A plan to improve the gold box is proposed and agreed upon |  | Completed
12 |  | Create a test case for this feature |  |  | Create a user story and test case for improving the level completion feedback |  |  |  | 1 | 1 | A user story and test case is made and found to be satisfactory by the team |  | Completed
13 |  | Implement the proposed changes |  |  | Implement software solution for proposed changes |  |  |  | 3 | 3 | The gold box is improved according to the plan proposed |  | Completed
14 |  | Complete test case from other team member |  |  | Have another team member test the code with the associated test case |  |  |  | 0.5 | 0.5 | Achieve a passing verdict on the test case made for this feature |  | Completed
15 |  | Comment code where applicable |  |  | Place comments in the code where applicable |  |  |  | 0.5 | 0.5 | Each section of the code is described clearly |  | Completed
16 | Adjust attack spawn location alignment | Find and gain an understanding of the code for player attacks | Michael Merritt | 1 | Read the documentation on player attacking and player projectiles | 2021-11-02 | 2021-11-09 | 2021-11-09 | 1 | 0.5 | Understand and be able to explain how the player attacks are spawned |  | Completed
17 |  | Create a test case for this feature |  |  | Create a user story and test case for improving the level completion feedback |  |  |  | 1 | 1 | A user story and test case is made and found to be satisfactory by the team |  | Completed
18 |  | Modify the projectile's spawn location to fit the player model |  |  | Change the player code to spawn the attack at the right location |  |  |  | 1 | 0.5 | The attack spawns at the cat's position rather than away from it |  | Completed
19 |  | Complete test case from other team member |  |  | Have another team member test the code with the associated test case |  |  |  | 0.5 | 0.5 | Achieve a passing verdict on the test case made for this feature |  | Completed
20 |  | Comment code where applicable |  |  | Place comments in the code where applicable |  |  |  | 0.5 | 0.5 | Each section of the code is described clearly |  | Completed
21 | Fix cat sprite mid air flip | Study the current code | Jonathan Mason | 1 | Read through and gain an understanding of the legacy code that involves the jumping mechanic | 2021-11-02 | 2021-11-09 | 2021-11-09 | 1 | 0.5 | Understand and be able to explain the code required to implement enchancement/bug fix |  | Completed
22 |  | Implement software solution |  |  | Make the cat sprite flip horizontally in air |  |  |  | 1 | 0.5 | The cat sprite flips when the opposite direction is input |  | Completed
23 |  | Complete test case from other team member |  |  | Have another team member test the code with the associated test case |  |  |  | 1 | 1 | Achieve a passing verdict on test case |  | Completed
24 |  | Comment code where applicable |  |  | Place comments in the code where applicable |  |  |  | 0.5 | 0.5 | Each section of the code is described clearly |  | Completed
25 | Fix attack animation after walking | Study the current code | Jonathan Mason | 1 | Read through and gain an understanding of the legacy code that involves the attacking and running mechanics. | 2021-11-04 | 2021-11-09 | 2021-11-04 | 0.5 | 0.5 | Understand and be able to explain the code required to implement enchancement/bug fix |  | Completed
26 |  | Implement software solution |  |  | Make the animation for walking stop when the user attacks, if the user is running. |  |  |  | 0.5 | 0.5 | The cat sprite does not continue walking if the user presses the attack button while walking. |  | Completed
27 |  | Complete test case from other team member |  |  | Have another team member test the code with the associated test case |  |  |  | 1 | 1 | Achieve a passing verdict on test case |  | Completed
28 |  | Comment code where applicable |  |  | Place comments in the code where applicable |  |  |  | 0.5 | 0.5 | Each section of the code is described clearly |  | Completed
29 | Improve attacking mid air/while mobile | Study current code | William Siri | 1 | Read through and gain and understanding of the legacy code that involves the jumping mechanic | 2021-11-02 | 2021-11-09 | 2021-11-09 | 1 | 0.5 | Understand and be able to explain the code required to implement enchancement/bug fix |  | Completed
30 |  | Implement software solution |  |  | Implement the ability for users to attack mid air or while mobile |  |  |  | 4 | 2.5 | The player is able to attack while jumping or moving |  | Completed
31 |  | Create a test case for attacking mid air |  |  | Create a test case for the new attacking ability |  |  |  | 0.5 | 0.5 | Test case follows all requirements and criteria |  | Completed
32 |  | Comment code where applicable |  |  | Have another team member test the code with the associated test case |  |  |  | 0.5 | 0.5 | Achieve a passing verdict on test case |  | Completed
33 | N/A | Merge code into master branch on GitHub | Michael Merritt | 1 | Merge all complete and working code into the master branch | 2021-11-09 | 2021-11-09 | 2021-11-10 | 1 | 2 | The code is successfully merged into the master branch | There were multiple merge conflicts that needed to be resolved for Player.java. | Completed
34 | N/A | Create presentation | All team members | 4 | Create a presentation on the progress made during the scrum cycle | 2021-11-09 | 2021-11-10 | 2021-11-10 | 3 | 2 | The presentation satifies all sections of the grading rubric |  | Completed
35 | N/A | Complete individual postmortems | All team members | 4 | Complete individual postmortems on Scrum Sprint 3 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 1 | 1 | All questions answer as outlined in the ScrumPostMortem.pdf on Blackboard |  | Completed
36 | N/A | Submit team postmortems | Michael Merritt | 1 | Submit the team's postmortems to the OneDrive | 2021-11-12 | 2021-11-12 | 2021-11-12 | 0.5 | 1 | All postmortems are complete and located in the OneDrive |  | Completed
37 | N/A | Update backlog | Michael Merritt | 1 | Update the backlog | 2021-11-12 | 2021-11-12 | 2021-11-12 | 0.5 | 0.5 | The backlog is updated |  | Completed
[8 empty] | Total | 41 | 32
|  | Team A3 |  |  | Scrum Cycle 4 |  |  | November 12th - Decemeber 3rd
Task (Prioritized) | Backlog item | Work Unit | Person(s) Responsible | # of People | Task Detail | Start Date | Due Date | Actual End Date | Estimated Time(hours) | Actual Time (hours) | Success Criteria | Obstacles | Results/Status
1 | N/A | Complete notable system improvement form | Michael Merritt | 1 | Write the notable system improvement | 2021-11-16 | 2021-11-16 | 2021-11-16 | 1 | 1 | The team and team manager approve |  | Completed
2 | Create Level 6 | Learn how to make a new level using the map editor | Omar Rosario | 1 | Read the documentation and code on the map editor, level selection, and scene transition code | 2021-11-16 | 2021-11-30 | 2021-11-27 | 2 | 1 | Understand and be able to explain how to make a new level in the game |  | Completed
3 |  | Propose a new level design |  |  | Decide on the structure, enemies, and obstacles in the new level |  |  | 2021-11-27 | 2 | 0.5 | A plan for the level is proposed and agreed upon |  | Completed
4 |  | Create a test case for Level 6 |  |  | Create test case for Level 6 |  |  | 2021-11-27 | 1 | 0.5 | Test case properly assesses level structure, enemies, and obstacles |  | Completed
5 |  | Develop Level 6 |  |  | Implement level structure, enemies, and obstacles |  |  | 2021-11-27 | 5 | 2 | Level 6 is implemented according to the proposed plan |  | Completed
6 |  | Complete test case from other team member |  |  | Have another member complete TC-15 |  |  | 2021-12-01 | 0.5 | 0.5 | Achieve a passing verdict on the test case made for Level 6 |  | Completed
7 |  | Comment code where applicable |  |  | Describe function of each implemented section of code |  |  | 2021-11-27 | 0.5 | 0.5 | Each section of code is described clearly |  | Completed
8 | Create level 7 | Learn how to make a new level using the map editor | Michael Merritt | 1 | Read the documentation and code on the map editor, level selection, and scene transition code | 2021-11-16 | 2021-11-26 | 2021-11-27 | 2 | 1 | Understand and be able to explain how to make a new level in the game |  | Completed
9 |  | Propose a new level design |  |  | Decide on the structure, enemies, and obstacles in the new level |  |  |  | 2 | 1 | A plan for the level is proposed and agreed upon |  | Completed
10 |  | Create a test case for this feature |  |  | Create a user story and test case for clearing the new level |  |  |  | 1 | 0.5 | A user story and test case is made and found to be satisfactory by the team |  | Completed
11 |  | Implement the proposed changes |  |  | Implement software solution for proposed changes |  |  |  | 3 | 2 | The level is implemented according to the plan proposed |  | Completed
12 |  | Complete test case from other team member |  |  | Have another team member test the code with the associated test case |  |  |  | 0.5 | 0.5 | Achieve a passing verdict on the test case made for this feature |  | Completed
13 |  | Comment code where applicable |  |  | Place comments in the code where applicable |  |  |  | 0.5 | 0.5 | Each section of the code is described clearly |  | Completed
14 | Check and restructure old levels to be more fun | Learn how to open and edit existing levels using the map editor | Michael Merritt | 1 | Read the documentation and code on editing levels using the map editor | 2021-11-16 | 2021-11-26 | 2021-11-27 | 2 | 1 | Understand and be able to explain how to make a new level in the game |  | Completed
15 |  | Identify unsatisfactory levels and propose new level designs for them |  |  | Play through all of the preexisting levels, determine which are good and which are bad, and come up with a plan on how to improve the bad ones |  |  |  | 2 | 2 | A plan for all unsatisfactory levels is proposed and agreed upon |  | Completed
16 |  | Create a test case for this feature |  |  | Create a user story and test case for clearing the redesigned levels |  |  |  | 1 | 0.5 | A user story and test case is made and found to be satisfactory by the team |  | Completed
17 |  | Implement the proposed changes |  |  | Implement software solution for proposed changes |  |  |  | 3 | 2 | The level is implemented according to the plan proposed |  | Completed
18 |  | Complete test case from other team member |  |  | Have another team member test the code with the associated test case |  |  |  | 0.5 | 0.5 | Achieve a passing verdict on the test case made for this feature |  | Completed
19 |  | Comment code where applicable |  |  | Place comments in the code where applicable |  |  |  | 0.5 | 0.5 | Each section of the code is described clearly |  | Completed
20 | Add more sound effects throughout the game | Identify parts of the game that would benefit from sound effects | Michael Merritt | 1 | Play through the game and come up with a list of events in the game which would be improved through the use of sound effects. | 2021-11-16 | 2021-11-26 | 2021-11-27 | 1 | 1 | Have a list of points in the game where sound effects should be added |  | Completed
21 |  | Create a test case for this feature |  |  | Create a user story and test case for testing the new sound effects |  |  |  | 1 | 0.5 | A user story and test case is made and found to be satisfactory by the team |  | Completed
22 |  | Generate and implement sound effects |  |  | Create and implement the new sound effects |  |  |  | 3 | 4 | All of the sound effects are implemented properly without breaking other systems | Picking the right sound effects took some time, and there were a couple bugs with sound effects being really loud or repeating instead of playing once | Completed
24 |  | Complete test case from other team member |  |  | Have another team member test the code with the associated test case |  |  |  | 0.5 | 0.5 | Achieve a passing verdict on the test case made for this feature |  | Completed
25 |  | Comment code where applicable |  |  | Place comments in the code where applicable |  |  |  | 0.5 | 0.5 | Each section of the code is described clearly |  | Completed
26 | Create music for the levels | Study the current code | Jonathan Mason | 1 | Read through and gain an understanding of the legacy code that involves the jumping mechanic | 2021-11-16 | 2021-11-26 | 2021-11-28 | 1 | 0.5 | Understand and be able to explain the code required to implement enchancement/bug fix |  | Completed
27 |  | Implement software solution |  |  | Find and/or make music. Add music to the game in the places where it is intended to be |  |  |  | 4 | 4 | The music plays when it should. If more than 1 song is added, the song changes correctly. | Title screen song would play on top of the game song when the game was started. The game music would start playing in the options menu and level select menu. | Completed
28 |  | Complete test case from other team member |  |  | Have another team member test the code with the associated test case |  |  |  | 1 | 0.5 | Achieve a passing verdict on test case |  | Completed
29 |  | Comment code where applicable |  |  | Place comments in the code where applicable |  |  |  | 0.5 | 0.5 | Each section of the code is described clearly |  | Completed
30 | Create level 8 | Learn how to make a new level using the map editor | Jonathan Mason | 1 | Read the documentation and code on editing levels using the map editor | 2021-11-16 | 2021-11-26 | 2021-11-28 | 0.5 | 0.5 | Understand and be able to explain how to make a new level in the game |  | Completed
31 |  | Propose a new level design |  |  | Decide on the structure, enemies, and obstacles in the new level |  |  |  | 2 | 1 | A plan for the level is proposed and agreed upon |  | Completed
32 |  | Implement the proposed changes |  |  | Implement software solution for proposed changes |  |  |  | 3 | 1 | The level is implemented according to the plan proposed |  | Completed
33 |  | Complete test case from other team member |  |  | Have another team member test the code with the associated test case |  |  |  | 0.5 | 0.5 | Achieve a passing verdict on test case |  | Completed
34 |  | Comment code where applicable |  |  | Place comments in the code where applicable |  |  |  | 0.5 | 0.5 | Each section of the code is described clearly |  | Completed
35 | Create level 9 | Learn how to make a new level using the map editor | William Siri | 1 | Read the documentation and code on editing levels using the map editor | 2021-11-16 | 2021-11-26 | 2021-11-28 | 0.5 | 0.5 | Understand and be able to explain how to make a new level in the game |  | Completed
36 |  | Propose a new level design |  |  | Decide on the structure, enemies, and obstacles in the new level |  |  |  | 2 | 1 | A plan for the level is proposed and agreed upon |  | Completed
37 |  | Implement the proposed changes |  |  | Implement software solution for proposed changes |  |  |  | 3 | 2 | The level is implemented according to the plan proposed |  | Completed
38 |  | Complete test case from other team member |  |  | Have another team member test the code with the associated test case |  |  |  | 0.5 | 0.5 | Achieve a passing verdict on test case |  | Completed
39 |  | Comment code where applicable |  |  | Place comments in the code where applicable |  |  |  | 0.5 | 0.5 | Each section of the code is described clearly |  | Completed
40 | Restructure Level Selection Screen | Study the current code | William Siri | 1 | Read through and gain an understanding of the legacy code that involves the level selection screen | 2021-11-16 | 2021-11-16 | 2021-11-16 | 0.5 | 0.5 | Understand and be able to explain the code required to implement enchancement/bug fix |  | Completed
41 |  | Implement software solution |  |  | Complete the code for the new implementation |  |  |  | 1.5 | 1.5 | Level Selection Screen is restructured corretly and is fully functional |  | Completed
42 |  | Create new test case for this fix |  |  | Create a new test case for the level selection restructure |  |  |  | 0.5 | 0.5 | Test case follows all criteria |  | Completed
43 |  | Have another team member complete the test case and merge changes to git |  |  | Have another team member complete the test case and merge changes to git |  |  |  | 0.5 | 0.5 | Achieve a passing verdict on test case |  | Completed
40 | N/A | Create presentation | All team members | 4 | Create a presentation on the progress made during the scrum cycle | 2021-12-01 | 2021-12-01 | 2021-12-01 | 3 | 3 | The presentation satifies all sections of the grading rubric |  | Completed
41 | N/A | Complete individual postmortems | All team members | 4 | Complete individual postmortems on Scrum Sprint 4 | 2021-12-03 | 2021-12-03 | 2021-12-02 | 1 | 1 | All questions answer as outlined in the ScrumPostMortem.pdf on Blackboard |  | Completed
42 | N/A | Submit team postmortems | Michael Merritt | 1 | Submit the team's postmortems to the OneDrive | 2021-12-03 | 2021-12-03 | 2021-12-02 | 0.5 | 0.5 | All postmortems are complete and located in the OneDrive |  | Completed
43 | N/A | Update backlog | Michael Merritt | 1 | Update the backlog | 2021-12-03 | 2021-12-03 | 2021-12-03 | 0.5 | 0.5 | The backlog is updated |  | Completed
[8 empty] | Total | 63.5 | 46